## Dashboard
YATRA — Master Plan Dashboard
4 parallel workstreams · 24 weeks · 168 days · India launch → Blitzscale
Phase 1 · Week 1–4 · Day 1–28 — Discover & Foundations
Exit criteria: 100 interviews · IRCTC ATA filed · All competitors audited · Dev foundation shipped · Sub-agent LOI
Phase 2 · Week 5–9 · Day 29–63 — Validate & Build Core
Exit criteria: Prototype NPS 60+ · 100 real bookings · Live tracking live · Voice < 15s · Flight + bus integrated
Phase 3 · Week 10–16 · Day 64–112 — Beta Launch & Iterate
Exit criteria: 500 users · 1,000 bookings · NPS 70+ · ATA approved · Enterprise LOI · Seed fundraise begins
Phase 4 · Week 17–24 · Day 113–168 — Scale & Fundraise
Exit criteria: 10K users · Seed closed · 3 enterprise contracts · Mumbai + Delhi live · Series A ready
Task count by stream
Stream 1 — Customer | 20 | tasks
Stream 2 — Stakeholder | 17 | tasks
Stream 3 — Research | 12 | tasks
Stream 4 — Dev | 21 | tasks
Stream S — Sync / Milestone | 12 | tasks
Day 168 — What Success Looks Like
✓ 10,000+ paying users
✓ ₹8Cr seed round closed
✓ 3+ enterprise contracts signed
✓ IRCTC ATA approved, on own booking quota
✓ Train + Bus + Flight + Taxi all integrated
✓ NPS 72+
✓ Agent personalisation learning from 50,000+ bookings
✓ Mumbai + Delhi waitlists open
✓ Series A materials ready
✓ Blitzscale engine running

## Master Plan
YATRA — Day-by-Day Master Plan ¦ 4 Parallel Workstreams ¦ Phase 1–4 ¦ 168 Days
Stream colours: 🟣 Customer (S1) 🟢 Stakeholder (S2) 🟠 Research (S3) 🔵 Dev (S4) ⬛ Sync/Milestone
Phase | Week | Day | Stream | Task | Detail / Actions | Owner | Deliverable | Status
PHASE 1 — DISCOVER & FOUNDATIONS · Week 1–4 · Day 1–28
Week 1
Phase 1 | Week 1 | Mon Day 1 | Stakeholder | Company incorporation — MCA filing | File Pvt Ltd on MCA portal. Appoint CA for PAN and GST simultaneously. COI arrives in 7–10 business days. | Founder | MCA acknowledgement receipt | To Do
Phase 1 | Week 1 | Mon Day 1 | Dev | Dev environment setup — monorepo, AWS, CI/CD | GitHub org, Turborepo, Expo React Native, Fastify API, PostgreSQL RDS, Redis. Sentry + Datadog from Day 1. First commit by EOD. | CTO | First commit pushed to GitHub | To Do
Phase 1 | Week 1 | Mon Day 1 | Research | Competitor app installs + first search on all 5 | Install MakeMyTrip, Ixigo, Cleartrip, IRCTC, RedBus. Run same search: BLR→MUM next Friday 2A. Screen record all. Note step counts and first impressions. | PM | Screen recordings + first-impressions doc | To Do
Phase 1 | Week 1 | Tue Day 2 | Customer | Interview recruitment — 150 LinkedIn DMs to IT professionals | Personalised DMs to Bengaluru IT sector (Infosys, TCS, Wipro, Accenture). Offer ₹200 Amazon voucher for 30-min interview. Track in Notion CRM. | Founder | 150 DMs sent, Notion CRM populated | To Do
Phase 1 | Week 1 | Tue Day 2 | Stakeholder | IRCTC ATA doc checklist + travel attorney engaged | Compile full ATA document checklist. Engage travel law attorney (budget ₹25,000). Brief on YATRA model. Request framing review before submission. | Founder | Attorney briefed, checklist complete | To Do
Phase 1 | Week 1 | Tue Day 2 | Research | MakeMyTrip full train booking audit | Complete end-to-end train booking on MMT (BLR→Chennai, this Friday, 2A). Count every step, screenshot every screen, note all upsells. Time from search to PNR. | PM | Annotated screenshot doc in Notion | To Do
Phase 1 | Week 1 | Wed Day 3 | Dev | Node.js API skeleton + PostgreSQL schema | Fastify API server. DB schema: users, trips, bookings, passengers, preferences, seat_watches. Prisma ORM. JWT auth. Swagger docs auto-generated. | CTO | API skeleton live, schema migrated | To Do
Phase 1 | Week 1 | Wed Day 3 | Customer | Interview script v1 — draft and finalise | 8-question script: last booking, time spent, worst moment, waitlist frustration, multi-app usage, ideal solution, price willingness, trust concerns. Calendly link live. | Founder | Script finalised, Calendly live | To Do
Phase 1 | Week 1 | Thu Day 4 | Research | IRCTC app deep audit — CAPTCHA, form fields, error states | Create test IRCTC account. Full booking attempt. Document: CAPTCHA mechanism, session timeout, every form field name + validation (critical for auto-fill), payment options, PNR screen. Feed to CTO Day 10. | PM | IRCTC form field mapping document | To Do
Phase 1 | Week 1 | Thu Day 4 | Stakeholder | IRCTC sandbox API access request sent | Apply at developer.irctc.co.in AND email irctcapi@irctc.co.in. Response time 5–15 business days. Start the clock today. | CTO | Application submitted, confirmation email saved | To Do
Phase 1 | Week 1 | Thu Day 4 | Dev | React Native app shell — navigation + core screens | Tab navigator: Home, Trips, Explore, Profile. Home with voice input button. Trip card component. Agent activity feed. Push notifications (Expo). Deploy to TestFlight + Android APK. | Mobile Dev | App navigable on TestFlight + APK | To Do
Phase 1 | Week 1 | Fri Day 5 | Customer | First 5 customer interviews run | 30-min Zoom sessions. Record with consent. No pitching — pure discovery. Focus on full story of worst booking experience. Debrief with co-founder after each. | Founder | 5 interviews recorded + notes in Notion | To Do
Phase 1 | Week 1 | Fri Day 5 | Research | Ixigo deep audit — WL prediction, live status, seat alerts | Test WL prediction accuracy on 5 real WL tickets. Compare live status vs NTES. Subscribe to 3 routes, measure alert latency. Tatkal booking test at 10am exactly. | PM | Ixigo vs IRCTC comparison doc | To Do
Phase 1 | Week 1 | Fri Day 5 | Sync / Milestone | WEEKLY SYNC — all 4 streams (every Friday 5pm, 30 min) | Agenda: (1) Customer top 3 insights (2) Stakeholders IRCTC status (3) Research findings for dev (4) Dev: shipped + blocked. All blockers to founder immediately. | All leads | Sync notes in Notion | To Do
Phase 1 | Week 1 | Sat Day 6 | Customer | Interview affinity mapping session | 3-hour Miro session. Group first 5 interview insights by theme. First version of top 5 pain points by frequency. These become core user stories. | Founder + PM | Affinity map in Miro, top 5 pain points | To Do
Phase 1 | Week 1 | Sat Day 6 | Stakeholder | IRCTC ATA application — draft review with attorney | Working session with attorney. Avoid 'automated'/'bot' language. Frame as user-initiated AI UX layer over IRCTC. Final draft target: ready to submit Day 10. | Founder + Attorney | ATA draft v1 reviewed | To Do
Phase 1 | Week 1 | Sun Day 7 | Sync / Milestone | Week 2 planning — interviews scheduled, dev sprint written | Confirm 15 interviews for Week 2. CTO writes Linear sprint tickets (IRCTC API target). PM schedules RedBus + Cleartrip audits. Founder IDs 3 ATAs for sub-agent outreach. | All founders | Week 2 sprint tickets in Linear | To Do
Week 2
Phase 1 | Week 2 | Mon Day 8 | Customer | 15 more interviews — 3 per day Mon–Fri (20 total by Fri) | From Day 10: introduce YATRA concept. 'Imagine saying book a train to Kochi and it does everything in 10 seconds — would that change how you travel?' Note trust + privacy scepticism. | Founder | 20 interviews completed, notes in Notion | To Do
Phase 1 | Week 2 | Mon Day 8 | Dev | IRCTC API integration begins (sandbox or documentation) | Build trainSearch() and getAvailability() endpoints. Mock responses where sandbox not yet live. Integration tests written. Document every IRCTC error code. | CTO | IRCTC search + availability endpoints working | To Do
Phase 1 | Week 2 | Tue Day 9 | Stakeholder | Sub-agent outreach — EaseMyTrip, Yatra.com, Akbar Travels | Email all 3 ATAs with 1-page YATRA deck. Propose 0.4% revenue share. Request 20-min intro call. Also post in TAAI LinkedIn group. LOI needed by Day 28. | Founder | 3 outreach emails sent + tracked | To Do
Phase 1 | Week 2 | Tue Day 9 | Research | RedBus technical audit — seat data + GPS tracking | Book real RedBus ticket (BLR→Mysore). Study real-time bus location refresh rate, seat selection UX, cancellation flow. Inspect network calls for API response structure. | PM | RedBus technical architecture notes | To Do
Phase 1 | Week 2 | Wed Day 10 | Stakeholder | 🔴 IRCTC ATA APPLICATION — FINAL SUBMISSION (cannot slip) | Registered post to IRCTC Commercial Dept New Delhi + email to irctccommercial@irctc.co.in. Get acknowledgement receipt. Processing window: Day 52–80 expected. Set Day 45 follow-up reminder. | Founder | ATA submitted, acknowledgement received — HIGH PRIORITY | To Do
Phase 1 | Week 2 | Wed Day 10 | Sync / Milestone | Dev-Research sync — IRCTC form field mapping | PM shares complete IRCTC form field audit with CTO. Map to DigiLocker data schema. Identify gaps. Build passenger auto-fill mapping table. 90 min prevents 2 weeks of integration bugs. | CTO + PM | Passenger field mapping table complete | To Do
Phase 1 | Week 2 | Thu Day 11 | Dev | DigiLocker OAuth integration — passenger data fetch | DigiLocker OAuth 2.0. Fetch Aadhaar (name, DOB, gender, address) and PAN. Encrypt in user profile. Build passenger pre-fill function: DigiLocker → IRCTC form fields. | CTO | DigiLocker fetch + passenger pre-fill working | To Do
Phase 1 | Week 2 | Thu Day 11 | Customer | Mid-week synthesis — 20 interviews, update pain point ranking | Check pattern consistency after 20 interviews. Update affinity map. Share top 5 insights with CTO. Key question: is waitlist anxiety or form fatigue the bigger pain? | Founder | Updated pain point ranking shared with CTO | To Do
Phase 1 | Week 2 | Fri Day 12 | Research | NTES live train tracking API study and comparison | Test RailwayAPI, Where Is My Train (RapidAPI), NTES direct. Compare latency, accuracy, cost, uptime. Document which data is real-time vs scheduled. Recommend primary + fallback to CTO. | PM | API comparison doc + recommendation | To Do
Phase 1 | Week 2 | Fri Day 12 | Dev | Razorpay UPI autopay — full sandbox integration | Mandate creation, silent debit API, webhook for payment confirmation, refund API. Full cycle tested in sandbox. 10-second cancellation window flow built. Test across GPay, PhonePe, Paytm, BHIM. | CTO | UPI autopay sandbox cycle working end-to-end | To Do
Phase 1 | Week 2 | Sat Day 13 | Customer | Waitlist landing page — build and launch | Framer or hand-coded: headline, 30-second demo screen recording, email capture. Live by EOD. Share in LinkedIn, Twitter, HasGeek Slack, NASSCOM groups. Target: 200 signups this weekend. | Founder + Mobile Dev | Landing page live, 200+ signups | To Do
Phase 1 | Week 2 | Sun Day 14 | Sync / Milestone | DPIIT startup recognition + Week 3 planning | Apply for DPIIT recognition online (free, 5–7 days). Plan Week 3: CTO = LLM intent engine. PM = Cleartrip + enterprise research. Founder = 15 more interviews. Sub-agent follow-ups. | All founders | DPIIT application filed, Week 3 sprint planned | To Do
Week 3
Phase 1 | Week 3 | Mon Day 15 | Dev | LLM intent engine v1 — Claude Sonnet structured output | Build NLU layer via Anthropic API. System prompt extracts: mode, origin, destination, date, class, passenger_count as JSON. Test 50 varied inputs. Accuracy target 95%+. Document all failure cases. | CTO | Intent engine parsing 95%+ of test inputs correctly | To Do
Phase 1 | Week 3 | Mon Day 15 | Customer | 15 more interviews (35 total) — concept validation focus | Directly pitch YATRA concept. 'We're building an app where you say book a train to Kochi and it handles everything in 10 seconds.' Probe: trust, data privacy fears, switching friction. | Founder | 35 interviews done, concept validation findings | To Do
Phase 1 | Week 3 | Tue Day 16 | Stakeholder | Sub-agent follow-up calls — escalate if email unanswered | Call main office numbers directly. Ask for partnerships team. Script: 'We're a new AI travel app seeking sub-agent relationship while ATA application processes — 500+ bookings/month expected.' Also TAAI forum post. | Founder | At least 1 intro meeting scheduled | To Do
Phase 1 | Week 3 | Tue Day 16 | Research | Cleartrip audit + myBiz enterprise deep-dive | Cleartrip full booking flow audit. Then myBiz: sign up for corporate trial. Test: approval workflow, policy settings, expense CSV export, multi-traveller booking, admin dashboard. Defines YATRA Enterprise feature spec. | PM | Cleartrip + myBiz feature comparison doc | To Do
Phase 1 | Week 3 | Wed Day 17 | Sync / Milestone | Dev-Research sync — LLM failure modes vs interview insights | CTO shares top 10 LLM parsing failures. PM cross-checks with real user utterances from interviews. Key decision: clarifying question for ambiguous dates OR pick nearest date? Interview data answers this. | CTO + PM | Ambiguous date handling decision documented | To Do
Phase 1 | Week 3 | Wed Day 17 | Dev | Google Calendar + Outlook OAuth — proactive travel detection | Read-only OAuth. NLP classifier for travel keywords in events. Proactive alert queue: 7 days before detected travel event. Max 1 proactive alert per user per day. | CTO | Calendar OAuth live, proactive alert queue working | To Do
Phase 1 | Week 3 | Thu Day 18 | Dev | Whisper API voice input integration | Hold-to-speak in React Native → Whisper API → transcript → LLM intent engine. Target: under 2 seconds from button release to intent extracted. Hindi + Tamil language detection. | Mobile Dev | Voice input working under 2s, Hindi + Tamil tested | To Do
Phase 1 | Week 3 | Thu Day 18 | Customer | Van Westendorp price sensitivity survey — launched to waitlist | 4 questions per price point: ₹99 / ₹149 / ₹249 / ₹499/month. Send to all 300+ waitlist members. 3-day collection period. Results confirm or adjust ₹149/mo pricing. | Founder | Survey live, responses collecting | To Do
Phase 1 | Week 3 | Fri Day 19 | Stakeholder | RedBus API partnership — first meeting | Present YATRA 1-pager. Ask: API access scope, seat inventory coverage, GPS data availability, commission rate, cancellation API. Information gathering only — no commitments. Follow-up within 24 hours. | Founder | Meeting notes + next steps doc | To Do
Phase 1 | Week 3 | Fri Day 19 | Sync / Milestone | WEEKLY SYNC — 40-interview milestone review | 40 interviews done. LLM engine v1 built. Calendar OAuth live. Voice input working. Sub-agent outreach in progress. Does data confirm top 5 pain points? Any surprise requiring product pivot discussion? | All leads | Sync notes, any pivots flagged | To Do
Week 4
Phase 1 | Week 4 | Mon Day 22 | Customer | Final 20 interviews — including 5 enterprise targets (100 total) | 4 interviews/day this week. Enterprise segment: HR managers + travel managers at IT companies. Ask: current travel tool, what's broken, would you pay ₹899/seat/month? First B2B validation data. | Founder | 100 interviews complete | To Do
Phase 1 | Week 4 | Mon Day 22 | Dev | Agent orchestrator v1 — state machine build | State machine: INTENT_PARSED → SEARCHING → RANKED → CONFIRMING (10s) → BOOKING → PAYING → CONFIRMED → FAILED. Each state: entry action, timeout, error handler, retry logic. | CTO | State machine built, first internal pipeline test | To Do
Phase 1 | Week 4 | Tue Day 23 | Stakeholder | Sub-agent deal — close or escalate to regional ATAs | By Day 23: at least one meeting should be scheduled. If all 3 still silent: call TAAI helpline, ask for regional Bengaluru ATA referrals. LOI signed by Day 28 = Phase 2 entry requirement. | Founder | Sub-agent LOI signed or final negotiation | To Do
Phase 1 | Week 4 | Tue Day 23 | Research | Competitor data architecture comparison document published | Master doc: how all 5 platforms handle search, availability, live tracking, payments, cancellation. Reference document for all YATRA architecture decisions. Shared with CTO immediately. | PM | Competitor architecture doc published + shared | To Do
Phase 1 | Week 4 | Wed Day 24 | Dev | INTERNAL ALPHA — first real booking, all founders test | All 4 founders make a real booking via sub-agent triggered by voice input. Document every error, latency, UX issue. Target under 30 seconds end-to-end. Most important Phase 1 milestone. | All founders | First real PNR confirmed via YATRA | To Do
Phase 1 | Week 4 | Wed Day 24 | Customer | 100-interview synthesis — final report | Full day: top 10 pain points ranked by frequency, 3 user personas (IT professional, leisure, enterprise), top 5 feature requests, price sensitivity findings, trust concerns list. Guides all decisions next 6 months. | Founder + PM | 100-interview synthesis report shared with team | To Do
Phase 1 | Week 4 | Thu Day 25 | Dev | Figma prototype v1 — 8 screens, 2 user flows | High-fidelity: home → voice input → agent thinking → confirmation card → calendar updated. Two flows: voice booking + proactive alert. For usability testing in Phase 2, not for development. | Mobile Dev | Figma prototype v1 shared with PM | To Do
Phase 1 | Week 4 | Thu Day 25 | Customer | LinkedIn paid campaign — ₹5,000 for 500+ waitlist signups | Bengaluru + Mumbai IT targeting. 25–40, frequent traveller job titles. 7-day run. Cost per signup target: under ₹10. Track via UTM parameters. | Founder | Campaign live, 500+ new signups | To Do
Phase 1 | Week 4 | Fri Day 26 | Sync / Milestone | PHASE 1 EXIT REVIEW — all 5 exit criteria must be ✓ | (1) 100 interviews ✓/✗ (2) IRCTC ATA submitted ✓/✗ (3) All 4 apps audited ✓/✗ (4) IRCTC search working in dev ✓/✗ (5) Sub-agent LOI signed or final negotiation ✓/✗. Any ✗ = do not advance. | All founders | Phase 1 exit checklist signed off | To Do
PHASE 2 — VALIDATE & BUILD CORE · Week 5–9 · Day 29–63
Week 5
Phase 2 | Week 5 | Mon Day 29 | Stakeholder | Sub-agent onboarding — first live booking via YATRA agent | Complete sub-agent technical onboarding. Get API credentials. Make first live booking through YATRA agent pipeline (founder's own real trip). Verify PNR issued + payment processed. | CTO + Founder | First real PNR via YATRA agent, sub-agent confirmed | To Do
Phase 2 | Week 5 | Mon Day 29 | Customer | Prototype usability sessions begin — 10 users this week | Recruit from interview pool (highest engagement respondents). 45-min sessions. Tasks: 'Book a train to Chennai this Friday' unassisted. Measure: task completion, time, confusion moments. Record all sessions. | Founder | 10 sessions recorded, findings noted | To Do
Phase 2 | Week 5 | Tue Day 30 | Dev | Seat watch agent — 30-min polling + auto-book build | Cron job: poll IRCTC availability every 30 min for watched routes. WL probability heuristic (WL number + days to departure + historical fill rate). Auto-book on availability + push notification. 3-day build. | CTO | Seat watch agent polling + auto-booking working | To Do
Phase 2 | Week 5 | Tue Day 30 | Research | Live tracking API comparison test — recommendation by Day 33 | Test 3 APIs: RailwayAPI, Where Is My Train, NTES direct. Compare latency, accuracy, cost, uptime. Test during a known delayed train. Deliver recommendation: primary + fallback. | PM | Live tracking API recommendation doc delivered | To Do
Phase 2 | Week 5 | Wed Day 31 | Stakeholder | IndiGo / Amadeus GDS — API introduction meeting | Contact Amadeus India (Gurugram). GDS covers all domestic airlines in one integration. Agenda: API scope, per-segment cost ($0.50–$2), sandbox timeline. Also email IndiGo Developer Relations directly. | Founder | Amadeus meeting notes, sandbox timeline confirmed | To Do
Phase 2 | Week 5 | Wed Day 31 | Sync / Milestone | Dev-Research sync — live tracking API decision | PM presents API comparison. CTO decides: primary = Where Is My Train API, fallback = NTES direct. Build abstraction layer so source can be swapped without code changes. | CTO + PM | Live tracking API decision documented, abstraction layer planned | To Do
Phase 2 | Week 5 | Thu Day 32 | Dev | Itinerary agent — Google Maps Places + Zomato integration | Post-booking itinerary generator. Input: destination + dates + preferences. Output: day-by-day plan via Google Maps Places API. Zomato API stub for restaurant reservations. Render as day cards. | Mobile Dev | Itinerary generator producing plans for test destinations | To Do
Phase 2 | Week 5 | Thu Day 32 | Customer | Prototype v1 findings → Figma v2 revised | After 10 sessions: identify top 5 UX issues. Expected: users want brief 'here's what I found' screen before auto-booking + more payment detail in confirmation. Apply changes. Re-test 5 more users. | Founder + Mobile Dev | Figma v2 with top issues resolved | To Do
Phase 2 | Week 5 | Fri Day 33 | Stakeholder | IRCTC ATA follow-up call — Day 23 of processing | Call IRCTC Commercial (+91-755-6610661). Ask for status. Get processing officer name. Mention DPIIT recognition. This is relationship building, not pressure. Document call notes carefully. | Founder | Call completed, officer name noted, relationship built | To Do
Week 6
Phase 2 | Week 6 | Days 36–42 | Customer | 50 prototype usability sessions complete. Waitlist hits 1,000. | All 50 sessions done. Synthesise findings. Pricing confirmed at ₹149/mo. Launch referral waitlist: 'Share link, jump the queue.' Send weekly email updates to waitlist members. | Founder | 50 sessions synthesised, 1,000+ waitlist signups | To Do
Phase 2 | Week 6 | Days 36–42 | Dev | All 4 founders make 10 real bookings via YATRA agent | Voice → PNR confirmed for all 10 bookings. Document every error, latency reading, UX issue. Target: under 20 seconds end-to-end. Most important dev milestone of Phase 2. | All founders | 10 successful real bookings, average time measured | To Do
Phase 2 | Week 6 | Days 36–42 | Stakeholder | RedBus API agreement signed. Amadeus sandbox access received. | RedBus deal: 2.5% revenue share. CTO begins RedBus integration. Ola Corporate API application filed. IRCTC: Week 4 of processing — no decision yet, expected Week 8–10. | Founder | RedBus LOI signed, Amadeus sandbox credentials received | To Do
Phase 2 | Week 6 | Days 36–42 | Research | DPDP Act compliance doc + Navan/TripActions enterprise teardown | All DPDP Act 2023 obligations documented for YATRA's data types. Feeds privacy policy and data architecture. Navan enterprise teardown: policy engine, approval flows, HRMS integration patterns. | PM | Compliance doc + enterprise teardown published | To Do
Week 7
Phase 2 | Week 7 | Days 43–49 | Customer | 5 enterprise discovery meetings — IT company HR/travel managers | Reach 10 companies, secure 5 meetings. Discovery only — no pitch. Key questions: current tool used, admin pain, per-seat budget, decision-maker identity. These feed Week 11 enterprise pilot conversations. | Founder | 5 enterprise meeting notes, budget + decision-maker data captured | To Do
Phase 2 | Week 7 | Days 43–49 | Dev | RedBus integration live + live train status in app | Bus search, booking, cancellation working. Live train status via Where Is My Train API in trip card. Auto-alert if train delayed 30+ minutes. Total modes: train + bus. | CTO | Multi-modal booking (train + bus) live end-to-end | To Do
Phase 2 | Week 7 | Days 43–49 | Stakeholder | IRCTC ATA Day 37 follow-up. Leverage any industry contacts. | Second follow-up call. Mention DPIIT recognition. Ask if additional documents needed. Warm intro to processing officer via any industry contact significantly speeds review. | Founder | Second call completed, any requested docs submitted | To Do
Week 8
Phase 2 | Week 8 | Days 50–56 | Dev | Amadeus GDS flight integration — all domestic airlines | Flight search, seat selection, booking, PNR fetch via Amadeus. Agent now routes: train vs bus vs flight based on user preference, price, duration. Multi-modal comparison card in UI. 20 test bookings. | CTO | All domestic flights bookable via YATRA | To Do
Phase 2 | Week 8 | Days 50–56 | Customer | 500 beta users selected from waitlist (1,500+ by now) | Criteria: 4+ trips/month, Bengaluru-based, mixed IT + leisure. Personalised email to each. WhatsApp beta community created. Beta launch: Week 10. | Founder | 500 beta users notified, WhatsApp community live | To Do
Phase 2 | Week 8 | Days 50–56 | Stakeholder | IRCTC ATA decision window — Week 6 of processing | Approvals typically arrive weeks 6–10. If approved: schedule IRCTC IT onboarding immediately, negotiate quota + terms. If not: escalate via DPIIT startup helpdesk. Sub-agent remains active fallback. | Founder | ATA decision received OR escalation filed | To Do
Week 9
Phase 2 | Week 9 | Days 57–63 | Dev | Beta hardening — load test 200 users, circuit breakers, P99 | Load test to 200 concurrent users. Circuit breakers for IRCTC daily 10–11am downtime. Graceful degradation messaging. P99 booking latency target: under 12 seconds. Crashlytics live. On-call rotation established. | CTO | 200-user load test passed, P99 under 12s | To Do
Phase 2 | Week 9 | Days 57–63 | Sync / Milestone | PHASE 2 EXIT REVIEW — all 6 exit criteria check | (1) Prototype NPS 60+ ✓/✗ (2) 100+ real bookings ✓/✗ (3) Live tracking in app ✓/✗ (4) Voice → booking under 15s ✓/✗ (5) 500 beta users notified ✓/✗ (6) RedBus + flights integrated ✓/✗. All ✓ = launch beta Day 64. | All founders | Phase 2 exit checklist signed off | To Do
PHASE 3 — BETA LAUNCH & ITERATE · Week 10–16 · Day 64–112
Week 10
Phase 3 | Week 10 | Mon Day 64 | Customer | 🚀 BETA LAUNCH — 500 users onboarded. Founder calls first 100. | Beta access emails sent to all 500. App on TestFlight + Android APK. Founder personally calls first 20 users for 5-min onboarding. Intercom live for in-app chat. First 100 = Founding Member status + lifetime 50% discount. | All founders | 500 users onboarded, first bookings made | To Do
Phase 3 | Week 10 | Days 65–70 | Dev | Daily: Datadog + Sentry review at 9am. Hotfix within 24 hours. | Any error affecting 5+ users → hotfix same day. Booking failure → personal message to affected user within 2 hours. Track: DAU, bookings/day, error rate, payment success rate. | CTO | Zero booking failures lasting more than 24 hours | To Do
Phase 3 | Week 10 | Days 65–70 | Customer | Friday weekly NPS pulse — 3 questions, every Friday | NPS (0–10), best thing this week, biggest frustration. Any NPS 0–6 = founder calls within 48 hours. Synthesise every Monday. Top complaint → dev sprint that week. Never skip. | Founder | First NPS baseline established | To Do
Weeks 11–12
Phase 3 | Weeks 11–12 | Days 71–84 | Stakeholder | Enterprise pilot LOI signed — 1st IT company (20 seats) | Convert best Week 7 discovery meeting into paid pilot. Offer: 20-seat pilot, 3 months at ₹499/seat (50% off). Success criteria agreed upfront. This is the Series A anchor proof point. | Founder | Enterprise LOI signed, pilot company onboarded | To Do
Phase 3 | Weeks 11–12 | Days 71–84 | Dev | Ola Corporate + DigiYatra — door-to-door achieved | Ola Corporate API: auto-book cab to station 45 mins before departure. DigiYatra: store user token, pass to airline at booking for facial recognition boarding. True door-to-door zero-touch delivered. | CTO | Cab auto-booking + DigiYatra boarding live | To Do
Phase 3 | Weeks 11–12 | Days 71–84 | Research | 1,000-booking dataset analysis — personalisation insights | Most common routes, class preferences, booking timing, cancellation rate. First real ML training signal for personalisation v2. Routes with consistent WL issues → prioritise for seat watch improvement. | PM | Booking data analysis report shared with CTO | To Do
Weeks 13–16
Phase 3 | Weeks 13–16 | Days 85–112 | Sync / Milestone | Seed fundraising — investor outreach begins | With 500 beta users + 1,000 bookings + enterprise LOI: approach Peak XV, Blume Ventures, Elevation Capital, Accel India. Prepare data room: metrics, user recordings, NPS, financial model. Target: term sheet by Day 112. | Founder | 5 investor decks sent, meetings scheduled | To Do
Phase 3 | Weeks 13–16 | Days 85–112 | Sync / Milestone | PHASE 3 EXIT REVIEW — Series A readiness | (1) 500+ active users ✓/✗ (2) 1,000+ bookings ✓/✗ (3) NPS 70+ ✓/✗ (4) IRCTC ATA approved ✓/✗ (5) Enterprise LOI signed ✓/✗ (6) Positive unit economics ✓/✗ (7) Seed round closed or final terms ✓/✗ | All founders | Phase 3 exit checklist + Series A readiness confirmed | To Do
PHASE 4 — SCALE & FUNDRAISE · Week 17–24 · Day 113–168
Weeks 17–18
Phase 4 | Weeks 17–18 | Days 113–126 | Customer | Referral programme launch + Mumbai waitlist open | Invite 3, get 3 months Pro free. In-app referral tracking. Mumbai waitlist: LinkedIn campaign targeting BKC, Andheri, Powai IT hubs. Target 5,000 Mumbai signups in 2 weeks. Delhi waitlist: Week 20. | Founder + Growth | Referral programme live, 5,000 Mumbai signups | To Do
Phase 4 | Weeks 17–18 | Days 113–126 | Dev | Enterprise dashboard v1 — policy engine + admin view | Corporate admin: travel policy settings, all employee trips view, CSV expense export, seat add/remove, travel blackout dates. Built directly from pilot company feedback. Converts pilots into 12-month contracts. | CTO | Enterprise dashboard live, pilot company using it | To Do
Phase 4 | Weeks 17–18 | Days 113–126 | Stakeholder | Air India + Vistara + DigiYatra full integration | Complete all domestic airline integrations. DigiYatra facial recognition boarding. KSRTC / MSRTC state bus direct APIs to reduce RedBus dependency for state routes. | Founder + CTO | All domestic airlines + state buses integrated | To Do
Weeks 19–24
Phase 4 | Weeks 19–24 | Days 127–168 | Research | SEA international expansion research | KAI Indonesia, KTM Malaysia, Thai Railways API mapping. Data residency requirements per country. Middle East corridor recovery analysis for Indian diaspora travel demand spike. | PM | SEA expansion research report, regulatory matrix by country | To Do
Phase 4 | Weeks 19–24 | Days 127–168 | Sync / Milestone | 10,000-user milestone + Series A preparation | With seed funding: hire 2 engineers, 1 growth, 1 customer success. Scale infra to 10K concurrent. LLM caching + batching for cost optimisation. Series A deck updated with 6 months of real metrics. Series A close target: Month 9–10. | All team | 10,000 paying users · ₹8Cr seed closed · 3+ enterprise contracts · Series A materials ready | To Do

## Stream 1 — Customer
Stream 1 — Customer Interaction & Feedback
Use filters to slice by Phase or Week. Update Status column as tasks complete.
Phase | Week | Task | Detail / Actions | Owner | Deliverable | Status
Phase 1 | Week 1 | Interview recruitment — 150 LinkedIn DMs to IT professionals | Personalised DMs to Bengaluru IT sector (Infosys, TCS, Wipro, Accenture). Offer ₹200 Amazon voucher for 30-min interview. Track in Notion CRM. | Founder | 150 DMs sent, Notion CRM populated | To Do
Phase 1 | Week 1 | Interview script v1 — draft and finalise | 8-question script: last booking, time spent, worst moment, waitlist frustration, multi-app usage, ideal solution, price willingness, trust concerns. Calendly link live. | Founder | Script finalised, Calendly live | To Do
Phase 1 | Week 1 | First 5 customer interviews run | 30-min Zoom sessions. Record with consent. No pitching — pure discovery. Focus on full story of worst booking experience. Debrief with co-founder after each. | Founder | 5 interviews recorded + notes in Notion | To Do
Phase 1 | Week 1 | Interview affinity mapping session | 3-hour Miro session. Group first 5 interview insights by theme. First version of top 5 pain points by frequency. These become core user stories. | Founder + PM | Affinity map in Miro, top 5 pain points | To Do
Phase 1 | Week 2 | 15 more interviews — 3 per day Mon–Fri (20 total by Fri) | From Day 10: introduce YATRA concept. 'Imagine saying book a train to Kochi and it does everything in 10 seconds — would that change how you travel?' Note trust + privacy scepticism. | Founder | 20 interviews completed, notes in Notion | To Do
Phase 1 | Week 2 | Mid-week synthesis — 20 interviews, update pain point ranking | Check pattern consistency after 20 interviews. Update affinity map. Share top 5 insights with CTO. Key question: is waitlist anxiety or form fatigue the bigger pain? | Founder | Updated pain point ranking shared with CTO | To Do
Phase 1 | Week 2 | Waitlist landing page — build and launch | Framer or hand-coded: headline, 30-second demo screen recording, email capture. Live by EOD. Share in LinkedIn, Twitter, HasGeek Slack, NASSCOM groups. Target: 200 signups this weekend. | Founder + Mobile Dev | Landing page live, 200+ signups | To Do
Phase 1 | Week 3 | 15 more interviews (35 total) — concept validation focus | Directly pitch YATRA concept. 'We're building an app where you say book a train to Kochi and it handles everything in 10 seconds.' Probe: trust, data privacy fears, switching friction. | Founder | 35 interviews done, concept validation findings | To Do
Phase 1 | Week 3 | Van Westendorp price sensitivity survey — launched to waitlist | 4 questions per price point: ₹99 / ₹149 / ₹249 / ₹499/month. Send to all 300+ waitlist members. 3-day collection period. Results confirm or adjust ₹149/mo pricing. | Founder | Survey live, responses collecting | To Do
Phase 1 | Week 4 | Final 20 interviews — including 5 enterprise targets (100 total) | 4 interviews/day this week. Enterprise segment: HR managers + travel managers at IT companies. Ask: current travel tool, what's broken, would you pay ₹899/seat/month? First B2B validation data. | Founder | 100 interviews complete | To Do
Phase 1 | Week 4 | 100-interview synthesis — final report | Full day: top 10 pain points ranked by frequency, 3 user personas (IT professional, leisure, enterprise), top 5 feature requests, price sensitivity findings, trust concerns list. Guides all decisions next 6 months. | Founder + PM | 100-interview synthesis report shared with team | To Do
Phase 1 | Week 4 | LinkedIn paid campaign — ₹5,000 for 500+ waitlist signups | Bengaluru + Mumbai IT targeting. 25–40, frequent traveller job titles. 7-day run. Cost per signup target: under ₹10. Track via UTM parameters. | Founder | Campaign live, 500+ new signups | To Do
Phase 2 | Week 5 | Prototype usability sessions begin — 10 users this week | Recruit from interview pool (highest engagement respondents). 45-min sessions. Tasks: 'Book a train to Chennai this Friday' unassisted. Measure: task completion, time, confusion moments. Record all sessions. | Founder | 10 sessions recorded, findings noted | To Do
Phase 2 | Week 5 | Prototype v1 findings → Figma v2 revised | After 10 sessions: identify top 5 UX issues. Expected: users want brief 'here's what I found' screen before auto-booking + more payment detail in confirmation. Apply changes. Re-test 5 more users. | Founder + Mobile Dev | Figma v2 with top issues resolved | To Do
Phase 2 | Week 6 | 50 prototype usability sessions complete. Waitlist hits 1,000. | All 50 sessions done. Synthesise findings. Pricing confirmed at ₹149/mo. Launch referral waitlist: 'Share link, jump the queue.' Send weekly email updates to waitlist members. | Founder | 50 sessions synthesised, 1,000+ waitlist signups | To Do
Phase 2 | Week 7 | 5 enterprise discovery meetings — IT company HR/travel managers | Reach 10 companies, secure 5 meetings. Discovery only — no pitch. Key questions: current tool used, admin pain, per-seat budget, decision-maker identity. These feed Week 11 enterprise pilot conversations. | Founder | 5 enterprise meeting notes, budget + decision-maker data captured | To Do
Phase 2 | Week 8 | 500 beta users selected from waitlist (1,500+ by now) | Criteria: 4+ trips/month, Bengaluru-based, mixed IT + leisure. Personalised email to each. WhatsApp beta community created. Beta launch: Week 10. | Founder | 500 beta users notified, WhatsApp community live | To Do
Phase 3 | Week 10 | 🚀 BETA LAUNCH — 500 users onboarded. Founder calls first 100. | Beta access emails sent to all 500. App on TestFlight + Android APK. Founder personally calls first 20 users for 5-min onboarding. Intercom live for in-app chat. First 100 = Founding Member status + lifetime 50% discount. | All founders | 500 users onboarded, first bookings made | To Do
Phase 3 | Week 10 | Friday weekly NPS pulse — 3 questions, every Friday | NPS (0–10), best thing this week, biggest frustration. Any NPS 0–6 = founder calls within 48 hours. Synthesise every Monday. Top complaint → dev sprint that week. Never skip. | Founder | First NPS baseline established | To Do
Phase 4 | Weeks 17–18 | Referral programme launch + Mumbai waitlist open | Invite 3, get 3 months Pro free. In-app referral tracking. Mumbai waitlist: LinkedIn campaign targeting BKC, Andheri, Powai IT hubs. Target 5,000 Mumbai signups in 2 weeks. Delhi waitlist: Week 20. | Founder + Growth | Referral programme live, 5,000 Mumbai signups | To Do

## Stream 2 — Stakeholders
Stream 2 — Stakeholder Meetings & Integration
Use filters to slice by Phase or Week. Update Status column as tasks complete.
Phase | Week | Task | Detail / Actions | Owner | Deliverable | Status
Phase 1 | Week 1 | Company incorporation — MCA filing | File Pvt Ltd on MCA portal. Appoint CA for PAN and GST simultaneously. COI arrives in 7–10 business days. | Founder | MCA acknowledgement receipt | To Do
Phase 1 | Week 1 | IRCTC ATA doc checklist + travel attorney engaged | Compile full ATA document checklist. Engage travel law attorney (budget ₹25,000). Brief on YATRA model. Request framing review before submission. | Founder | Attorney briefed, checklist complete | To Do
Phase 1 | Week 1 | IRCTC sandbox API access request sent | Apply at developer.irctc.co.in AND email irctcapi@irctc.co.in. Response time 5–15 business days. Start the clock today. | CTO | Application submitted, confirmation email saved | To Do
Phase 1 | Week 1 | IRCTC ATA application — draft review with attorney | Working session with attorney. Avoid 'automated'/'bot' language. Frame as user-initiated AI UX layer over IRCTC. Final draft target: ready to submit Day 10. | Founder + Attorney | ATA draft v1 reviewed | To Do
Phase 1 | Week 2 | Sub-agent outreach — EaseMyTrip, Yatra.com, Akbar Travels | Email all 3 ATAs with 1-page YATRA deck. Propose 0.4% revenue share. Request 20-min intro call. Also post in TAAI LinkedIn group. LOI needed by Day 28. | Founder | 3 outreach emails sent + tracked | To Do
Phase 1 | Week 2 | 🔴 IRCTC ATA APPLICATION — FINAL SUBMISSION (cannot slip) | Registered post to IRCTC Commercial Dept New Delhi + email to irctccommercial@irctc.co.in. Get acknowledgement receipt. Processing window: Day 52–80 expected. Set Day 45 follow-up reminder. | Founder | ATA submitted, acknowledgement received — HIGH PRIORITY | To Do
Phase 1 | Week 3 | Sub-agent follow-up calls — escalate if email unanswered | Call main office numbers directly. Ask for partnerships team. Script: 'We're a new AI travel app seeking sub-agent relationship while ATA application processes — 500+ bookings/month expected.' Also TAAI forum post. | Founder | At least 1 intro meeting scheduled | To Do
Phase 1 | Week 3 | RedBus API partnership — first meeting | Present YATRA 1-pager. Ask: API access scope, seat inventory coverage, GPS data availability, commission rate, cancellation API. Information gathering only — no commitments. Follow-up within 24 hours. | Founder | Meeting notes + next steps doc | To Do
Phase 1 | Week 4 | Sub-agent deal — close or escalate to regional ATAs | By Day 23: at least one meeting should be scheduled. If all 3 still silent: call TAAI helpline, ask for regional Bengaluru ATA referrals. LOI signed by Day 28 = Phase 2 entry requirement. | Founder | Sub-agent LOI signed or final negotiation | To Do
Phase 2 | Week 5 | Sub-agent onboarding — first live booking via YATRA agent | Complete sub-agent technical onboarding. Get API credentials. Make first live booking through YATRA agent pipeline (founder's own real trip). Verify PNR issued + payment processed. | CTO + Founder | First real PNR via YATRA agent, sub-agent confirmed | To Do
Phase 2 | Week 5 | IndiGo / Amadeus GDS — API introduction meeting | Contact Amadeus India (Gurugram). GDS covers all domestic airlines in one integration. Agenda: API scope, per-segment cost ($0.50–$2), sandbox timeline. Also email IndiGo Developer Relations directly. | Founder | Amadeus meeting notes, sandbox timeline confirmed | To Do
Phase 2 | Week 5 | IRCTC ATA follow-up call — Day 23 of processing | Call IRCTC Commercial (+91-755-6610661). Ask for status. Get processing officer name. Mention DPIIT recognition. This is relationship building, not pressure. Document call notes carefully. | Founder | Call completed, officer name noted, relationship built | To Do
Phase 2 | Week 6 | RedBus API agreement signed. Amadeus sandbox access received. | RedBus deal: 2.5% revenue share. CTO begins RedBus integration. Ola Corporate API application filed. IRCTC: Week 4 of processing — no decision yet, expected Week 8–10. | Founder | RedBus LOI signed, Amadeus sandbox credentials received | To Do
Phase 2 | Week 7 | IRCTC ATA Day 37 follow-up. Leverage any industry contacts. | Second follow-up call. Mention DPIIT recognition. Ask if additional documents needed. Warm intro to processing officer via any industry contact significantly speeds review. | Founder | Second call completed, any requested docs submitted | To Do
Phase 2 | Week 8 | IRCTC ATA decision window — Week 6 of processing | Approvals typically arrive weeks 6–10. If approved: schedule IRCTC IT onboarding immediately, negotiate quota + terms. If not: escalate via DPIIT startup helpdesk. Sub-agent remains active fallback. | Founder | ATA decision received OR escalation filed | To Do
Phase 3 | Weeks 11–12 | Enterprise pilot LOI signed — 1st IT company (20 seats) | Convert best Week 7 discovery meeting into paid pilot. Offer: 20-seat pilot, 3 months at ₹499/seat (50% off). Success criteria agreed upfront. This is the Series A anchor proof point. | Founder | Enterprise LOI signed, pilot company onboarded | To Do
Phase 4 | Weeks 17–18 | Air India + Vistara + DigiYatra full integration | Complete all domestic airline integrations. DigiYatra facial recognition boarding. KSRTC / MSRTC state bus direct APIs to reduce RedBus dependency for state routes. | Founder + CTO | All domestic airlines + state buses integrated | To Do

## Stream 3 — Research
Stream 3 — Market & Technical Research
Use filters to slice by Phase or Week. Update Status column as tasks complete.
Phase | Week | Task | Detail / Actions | Owner | Deliverable | Status
Phase 1 | Week 1 | Competitor app installs + first search on all 5 | Install MakeMyTrip, Ixigo, Cleartrip, IRCTC, RedBus. Run same search: BLR→MUM next Friday 2A. Screen record all. Note step counts and first impressions. | PM | Screen recordings + first-impressions doc | To Do
Phase 1 | Week 1 | MakeMyTrip full train booking audit | Complete end-to-end train booking on MMT (BLR→Chennai, this Friday, 2A). Count every step, screenshot every screen, note all upsells. Time from search to PNR. | PM | Annotated screenshot doc in Notion | To Do
Phase 1 | Week 1 | IRCTC app deep audit — CAPTCHA, form fields, error states | Create test IRCTC account. Full booking attempt. Document: CAPTCHA mechanism, session timeout, every form field name + validation (critical for auto-fill), payment options, PNR screen. Feed to CTO Day 10. | PM | IRCTC form field mapping document | To Do
Phase 1 | Week 1 | Ixigo deep audit — WL prediction, live status, seat alerts | Test WL prediction accuracy on 5 real WL tickets. Compare live status vs NTES. Subscribe to 3 routes, measure alert latency. Tatkal booking test at 10am exactly. | PM | Ixigo vs IRCTC comparison doc | To Do
Phase 1 | Week 2 | RedBus technical audit — seat data + GPS tracking | Book real RedBus ticket (BLR→Mysore). Study real-time bus location refresh rate, seat selection UX, cancellation flow. Inspect network calls for API response structure. | PM | RedBus technical architecture notes | To Do
Phase 1 | Week 2 | NTES live train tracking API study and comparison | Test RailwayAPI, Where Is My Train (RapidAPI), NTES direct. Compare latency, accuracy, cost, uptime. Document which data is real-time vs scheduled. Recommend primary + fallback to CTO. | PM | API comparison doc + recommendation | To Do
Phase 1 | Week 3 | Cleartrip audit + myBiz enterprise deep-dive | Cleartrip full booking flow audit. Then myBiz: sign up for corporate trial. Test: approval workflow, policy settings, expense CSV export, multi-traveller booking, admin dashboard. Defines YATRA Enterprise feature spec. | PM | Cleartrip + myBiz feature comparison doc | To Do
Phase 1 | Week 4 | Competitor data architecture comparison document published | Master doc: how all 5 platforms handle search, availability, live tracking, payments, cancellation. Reference document for all YATRA architecture decisions. Shared with CTO immediately. | PM | Competitor architecture doc published + shared | To Do
Phase 2 | Week 5 | Live tracking API comparison test — recommendation by Day 33 | Test 3 APIs: RailwayAPI, Where Is My Train, NTES direct. Compare latency, accuracy, cost, uptime. Test during a known delayed train. Deliver recommendation: primary + fallback. | PM | Live tracking API recommendation doc delivered | To Do
Phase 2 | Week 6 | DPDP Act compliance doc + Navan/TripActions enterprise teardown | All DPDP Act 2023 obligations documented for YATRA's data types. Feeds privacy policy and data architecture. Navan enterprise teardown: policy engine, approval flows, HRMS integration patterns. | PM | Compliance doc + enterprise teardown published | To Do
Phase 3 | Weeks 11–12 | 1,000-booking dataset analysis — personalisation insights | Most common routes, class preferences, booking timing, cancellation rate. First real ML training signal for personalisation v2. Routes with consistent WL issues → prioritise for seat watch improvement. | PM | Booking data analysis report shared with CTO | To Do
Phase 4 | Weeks 19–24 | SEA international expansion research | KAI Indonesia, KTM Malaysia, Thai Railways API mapping. Data residency requirements per country. Middle East corridor recovery analysis for Indian diaspora travel demand spike. | PM | SEA expansion research report, regulatory matrix by country | To Do

## Stream 4 — Dev
Stream 4 — Development
Use filters to slice by Phase or Week. Update Status column as tasks complete.
Phase | Week | Task | Detail / Actions | Owner | Deliverable | Status
Phase 1 | Week 1 | Dev environment setup — monorepo, AWS, CI/CD | GitHub org, Turborepo, Expo React Native, Fastify API, PostgreSQL RDS, Redis. Sentry + Datadog from Day 1. First commit by EOD. | CTO | First commit pushed to GitHub | To Do
Phase 1 | Week 1 | Node.js API skeleton + PostgreSQL schema | Fastify API server. DB schema: users, trips, bookings, passengers, preferences, seat_watches. Prisma ORM. JWT auth. Swagger docs auto-generated. | CTO | API skeleton live, schema migrated | To Do
Phase 1 | Week 1 | React Native app shell — navigation + core screens | Tab navigator: Home, Trips, Explore, Profile. Home with voice input button. Trip card component. Agent activity feed. Push notifications (Expo). Deploy to TestFlight + Android APK. | Mobile Dev | App navigable on TestFlight + APK | To Do
Phase 1 | Week 2 | IRCTC API integration begins (sandbox or documentation) | Build trainSearch() and getAvailability() endpoints. Mock responses where sandbox not yet live. Integration tests written. Document every IRCTC error code. | CTO | IRCTC search + availability endpoints working | To Do
Phase 1 | Week 2 | DigiLocker OAuth integration — passenger data fetch | DigiLocker OAuth 2.0. Fetch Aadhaar (name, DOB, gender, address) and PAN. Encrypt in user profile. Build passenger pre-fill function: DigiLocker → IRCTC form fields. | CTO | DigiLocker fetch + passenger pre-fill working | To Do
Phase 1 | Week 2 | Razorpay UPI autopay — full sandbox integration | Mandate creation, silent debit API, webhook for payment confirmation, refund API. Full cycle tested in sandbox. 10-second cancellation window flow built. Test across GPay, PhonePe, Paytm, BHIM. | CTO | UPI autopay sandbox cycle working end-to-end | To Do
Phase 1 | Week 3 | LLM intent engine v1 — Claude Sonnet structured output | Build NLU layer via Anthropic API. System prompt extracts: mode, origin, destination, date, class, passenger_count as JSON. Test 50 varied inputs. Accuracy target 95%+. Document all failure cases. | CTO | Intent engine parsing 95%+ of test inputs correctly | To Do
Phase 1 | Week 3 | Google Calendar + Outlook OAuth — proactive travel detection | Read-only OAuth. NLP classifier for travel keywords in events. Proactive alert queue: 7 days before detected travel event. Max 1 proactive alert per user per day. | CTO | Calendar OAuth live, proactive alert queue working | To Do
Phase 1 | Week 3 | Whisper API voice input integration | Hold-to-speak in React Native → Whisper API → transcript → LLM intent engine. Target: under 2 seconds from button release to intent extracted. Hindi + Tamil language detection. | Mobile Dev | Voice input working under 2s, Hindi + Tamil tested | To Do
Phase 1 | Week 4 | Agent orchestrator v1 — state machine build | State machine: INTENT_PARSED → SEARCHING → RANKED → CONFIRMING (10s) → BOOKING → PAYING → CONFIRMED → FAILED. Each state: entry action, timeout, error handler, retry logic. | CTO | State machine built, first internal pipeline test | To Do
Phase 1 | Week 4 | INTERNAL ALPHA — first real booking, all founders test | All 4 founders make a real booking via sub-agent triggered by voice input. Document every error, latency, UX issue. Target under 30 seconds end-to-end. Most important Phase 1 milestone. | All founders | First real PNR confirmed via YATRA | To Do
Phase 1 | Week 4 | Figma prototype v1 — 8 screens, 2 user flows | High-fidelity: home → voice input → agent thinking → confirmation card → calendar updated. Two flows: voice booking + proactive alert. For usability testing in Phase 2, not for development. | Mobile Dev | Figma prototype v1 shared with PM | To Do
Phase 2 | Week 5 | Seat watch agent — 30-min polling + auto-book build | Cron job: poll IRCTC availability every 30 min for watched routes. WL probability heuristic (WL number + days to departure + historical fill rate). Auto-book on availability + push notification. 3-day build. | CTO | Seat watch agent polling + auto-booking working | To Do
Phase 2 | Week 5 | Itinerary agent — Google Maps Places + Zomato integration | Post-booking itinerary generator. Input: destination + dates + preferences. Output: day-by-day plan via Google Maps Places API. Zomato API stub for restaurant reservations. Render as day cards. | Mobile Dev | Itinerary generator producing plans for test destinations | To Do
Phase 2 | Week 6 | All 4 founders make 10 real bookings via YATRA agent | Voice → PNR confirmed for all 10 bookings. Document every error, latency reading, UX issue. Target: under 20 seconds end-to-end. Most important dev milestone of Phase 2. | All founders | 10 successful real bookings, average time measured | To Do
Phase 2 | Week 7 | RedBus integration live + live train status in app | Bus search, booking, cancellation working. Live train status via Where Is My Train API in trip card. Auto-alert if train delayed 30+ minutes. Total modes: train + bus. | CTO | Multi-modal booking (train + bus) live end-to-end | To Do
Phase 2 | Week 8 | Amadeus GDS flight integration — all domestic airlines | Flight search, seat selection, booking, PNR fetch via Amadeus. Agent now routes: train vs bus vs flight based on user preference, price, duration. Multi-modal comparison card in UI. 20 test bookings. | CTO | All domestic flights bookable via YATRA | To Do
Phase 2 | Week 9 | Beta hardening — load test 200 users, circuit breakers, P99 | Load test to 200 concurrent users. Circuit breakers for IRCTC daily 10–11am downtime. Graceful degradation messaging. P99 booking latency target: under 12 seconds. Crashlytics live. On-call rotation established. | CTO | 200-user load test passed, P99 under 12s | To Do
Phase 3 | Week 10 | Daily: Datadog + Sentry review at 9am. Hotfix within 24 hours. | Any error affecting 5+ users → hotfix same day. Booking failure → personal message to affected user within 2 hours. Track: DAU, bookings/day, error rate, payment success rate. | CTO | Zero booking failures lasting more than 24 hours | To Do
Phase 3 | Weeks 11–12 | Ola Corporate + DigiYatra — door-to-door achieved | Ola Corporate API: auto-book cab to station 45 mins before departure. DigiYatra: store user token, pass to airline at booking for facial recognition boarding. True door-to-door zero-touch delivered. | CTO | Cab auto-booking + DigiYatra boarding live | To Do
Phase 4 | Weeks 17–18 | Enterprise dashboard v1 — policy engine + admin view | Corporate admin: travel policy settings, all employee trips view, CSV expense export, seat add/remove, travel blackout dates. Built directly from pilot company feedback. Converts pilots into 12-month contracts. | CTO | Enterprise dashboard live, pilot company using it | To Do

## Milestones & Syncs
YATRA — Milestones, Exit Criteria & Weekly Syncs
Phase exit criteria must ALL be ✓ before advancing. Weekly syncs are non-negotiable every Friday 5pm.
Phase | Week | Item | Detail | Owner | Success Metric | Status
Phase 1 | Week 1 | WEEKLY SYNC — all 4 streams (every Friday 5pm, 30 min) | Agenda: (1) Customer top 3 insights (2) Stakeholders IRCTC status (3) Research findings for dev (4) Dev: shipped + blocked. All blockers to founder immediately. | All leads | Sync notes in Notion | Pending
Phase 1 | Week 1 | Week 2 planning — interviews scheduled, dev sprint written | Confirm 15 interviews for Week 2. CTO writes Linear sprint tickets (IRCTC API target). PM schedules RedBus + Cleartrip audits. Founder IDs 3 ATAs for sub-agent outreach. | All founders | Week 2 sprint tickets in Linear | Pending
Phase 1 | Week 2 | Dev-Research sync — IRCTC form field mapping | PM shares complete IRCTC form field audit with CTO. Map to DigiLocker data schema. Identify gaps. Build passenger auto-fill mapping table. 90 min prevents 2 weeks of integration bugs. | CTO + PM | Passenger field mapping table complete | Pending
Phase 1 | Week 2 | DPIIT startup recognition + Week 3 planning | Apply for DPIIT recognition online (free, 5–7 days). Plan Week 3: CTO = LLM intent engine. PM = Cleartrip + enterprise research. Founder = 15 more interviews. Sub-agent follow-ups. | All founders | DPIIT application filed, Week 3 sprint planned | Pending
Phase 1 | Week 3 | Dev-Research sync — LLM failure modes vs interview insights | CTO shares top 10 LLM parsing failures. PM cross-checks with real user utterances from interviews. Key decision: clarifying question for ambiguous dates OR pick nearest date? Interview data answers this. | CTO + PM | Ambiguous date handling decision documented | Pending
Phase 1 | Week 3 | WEEKLY SYNC — 40-interview milestone review | 40 interviews done. LLM engine v1 built. Calendar OAuth live. Voice input working. Sub-agent outreach in progress. Does data confirm top 5 pain points? Any surprise requiring product pivot discussion? | All leads | Sync notes, any pivots flagged | Pending
Phase 1 | Week 4 | PHASE 1 EXIT REVIEW — all 5 exit criteria must be ✓ | (1) 100 interviews ✓/✗ (2) IRCTC ATA submitted ✓/✗ (3) All 4 apps audited ✓/✗ (4) IRCTC search working in dev ✓/✗ (5) Sub-agent LOI signed or final negotiation ✓/✗. Any ✗ = do not advance. | All founders | Phase 1 exit checklist signed off | Pending
Phase 2 | Week 5 | Dev-Research sync — live tracking API decision | PM presents API comparison. CTO decides: primary = Where Is My Train API, fallback = NTES direct. Build abstraction layer so source can be swapped without code changes. | CTO + PM | Live tracking API decision documented, abstraction layer planned | Pending
Phase 2 | Week 9 | PHASE 2 EXIT REVIEW — all 6 exit criteria check | (1) Prototype NPS 60+ ✓/✗ (2) 100+ real bookings ✓/✗ (3) Live tracking in app ✓/✗ (4) Voice → booking under 15s ✓/✗ (5) 500 beta users notified ✓/✗ (6) RedBus + flights integrated ✓/✗. All ✓ = launch beta Day 64. | All founders | Phase 2 exit checklist signed off | Pending
Phase 3 | Weeks 13–16 | Seed fundraising — investor outreach begins | With 500 beta users + 1,000 bookings + enterprise LOI: approach Peak XV, Blume Ventures, Elevation Capital, Accel India. Prepare data room: metrics, user recordings, NPS, financial model. Target: term sheet by Day 112. | Founder | 5 investor decks sent, meetings scheduled | Pending
Phase 3 | Weeks 13–16 | PHASE 3 EXIT REVIEW — Series A readiness | (1) 500+ active users ✓/✗ (2) 1,000+ bookings ✓/✗ (3) NPS 70+ ✓/✗ (4) IRCTC ATA approved ✓/✗ (5) Enterprise LOI signed ✓/✗ (6) Positive unit economics ✓/✗ (7) Seed round closed or final terms ✓/✗ | All founders | Phase 3 exit checklist + Series A readiness confirmed | Pending
Phase 4 | Weeks 19–24 | 10,000-user milestone + Series A preparation | With seed funding: hire 2 engineers, 1 growth, 1 customer success. Scale infra to 10K concurrent. LLM caching + batching for cost optimisation. Series A deck updated with 6 months of real metrics. Series A close target: Month 9–10. | All team | 10,000 paying users · ₹8Cr seed closed · 3+ enterprise contracts · Series A materials ready | Pending